## Instruction
Accredited Checker Value Articulation Framework |  |  | version 1.0 | 2026-09-01
Development Revision
Date | Vers | Development Revision | By | Remark
16.09.2026 | 0.1 | Initial Draft shared with BCA | JSN | For feedback
19.09.2027 | 0.2 | Revision to be shared with BCA | JSN | For final feedback

## Project Data
Description | Sub Item | Input | Notes
|  |  |  | REF | Approved Use of Development - Definition
Project Detail | Project Name | HDB Rediential Block Development
| Client | HDB
| Project Period | Jan 2027-Jan 2030
| Complexity | Medium | Low, Medium, High
Total GFA (m2) |  | 60000
Site Area (m2) |  | 100000
Project Type | Residential (Public or Private) |  | Public
(ref to BCA Defn) | Commercial (Office, Retail, Hotel)
Industrial
Institution (Civic & Community, Sports & Recreation)
Healthcare & Medical Care
Infrastructure
Utility
Addition & Alteration
Asset Enhancement
Contract Type | Engineer's Design
Design & Build
Develop and Construct
Project Stages & Duration | 0 - Project Mobilisation | 4
(in months) | 1 -Overall Design Review Task | 9
(include contingency) | 2 - Foundation Design | 17 | AC Checklist
| 3 - Building Structural System | 20 | AC Checklist
| 4 - Building with Specialised Structures | 32 | AC Checklist
| 5 - Earth Retaining Structures | 11 | AC Checklist
| 6 - Specific Structural Elements | 11 | AC Checklist
Manday Rates | Director / Principal
Accredited Checker (if not director)
Senior Associate Director
Associate Director
Senior Professional Staff (>10yrs)
Professional Staff (<10yrs)

## AC VAF Low C
Accredited Checker (AC) Value Articulation Framework (VAF) |  |  |  | version 0.2
Project |  | XYZ Project | By | Er ACES
Client |  | HDB | Date | 2026-09-01
Period |  | Jan 2027-Jan 2030
Category of Project |  | Low - 2 blocks of 14 storey HDB Flat with 1 MSCP
[6 empty] | Program Unit | Hours | Resource Unit |  |  | Days
Project Stages |  | Tasks / Remarks | BCA Items of Services - Milestone (Reference to SCA) |  |  | Budget | Programme | Resources (Hours, Days, Weeks) | [9 empty] | Remarks
Stage | Sub-stage | Tasks / Remarks | ID | BCA Payment Milestone / Tasks | % fee | % of fee | Hours | Director / Principal | Accredited Checker (if not director) | Senior Associate Director | Associate Director | Senior Professional Staff (>10yrs) | Professional Staff (<10yrs)
0 - Project Mobilisation | Project preparation | Project Proposal and Setup including Quality and Verification Plan, Resource Plan, Work Breakdown Structure, Communication Plan | [5 empty] | 1 | 1 | 2 |  |  | 1
|  | Project team briefing and kick off | [5 empty] | 1 | 1 | 2 |  |  | 1
|  | Project Risk Assessment and Management plan | [5 empty] | 1 |  | 2 |  |  | 1
|  | Finance - Cashflow and invoicing plan | [5 empty] | 1 |  | 2 |  |  | 1
1 - Overall Design Review Tasks | Global Review of the Techincal Approach | Code of Practice | [6 empty] | 2 | 2 |  |  | 2
Design Loadings
Strucutral Analysis
Stability and Robustness
All Key Structural Elements
Architectural and Structural Drawings
Review of Soil report and Geotechnical Interpretation Report
Expert Reviewer is required
Other Aspects in Design
2 - Foundation design | Foundation Loads | Appropriate values of dead, live ,wind and notional loads have been used | [6 empty] | 1 | 1 |  |  | 1
|  | Column loads have been appropriately computed | [6 empty] | 1 | 1 |  |  | 5
|  | Effects of wind and notional loads on the building or structure have been checked | [6 empty] | 1 | 1 |  |  | 3
|  | Comparison of the loading computation by the QP & AC has been carried out | [6 empty] | 1 | 1 |  |  | 2
| Piles | Piles have been designed for skin friction and end bearing capacities | [6 empty] | 1 | 1 |  |  | 5
|  | Piles have been designed for lateral loads and bending moment | [6 empty] | 1 | 1 |  |  | 2
Pile joints have been designed for
|  | Piles have been designed for uplift | [6 empty] | 1 | 1 |  |  | 2
Socketings have been designed for piles with short penetration depths
|  | Piles have been designed for negative skin friction | [6 empty] | 1 | 1 |  |  | 2
|  | Determine design pile settlement for building and impact on the main structures | [6 empty] | 1 | 1 |  |  | 2
| Raft/footing | Appropriate allowable bearing capacity of soil has been assumed in design | [6 empty] | 1 | 1 |  |  | 2
Appropriate modulus of sub-grade reaction of the soil has been assumed in design
Appropriate model used for structural analysis of the raft with appropriate loadings
The raft has been designed to resist punching shear from columns
|  | The building or structure has been designed to cater for probable differential and total settlement. | [6 empty] | 1 | 1 |  |  | 2
Review of plate load test results against design soil bearing capacity
3 - Building / Structural System | Building of less than 30 Storey | Designed for wind loads | [6 empty] | 1 | 1 |  |  | 10
Designed for notional loads
|  | Stability system has been identified and evaluated to be adequate and robust | [6 empty] | 1 | 1 |  |  | 5
Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions
|  | Provided adequate internal and peripheral ties at floor levels | [6 empty] | 1 | 1 |  |  | 5
Designed for capacities to resist base overturning moment and base shear
|  | Designed for building sway (p-delta effect) | [6 empty] | 1 | 1 |  |  | 5
| Building of more than 30 storey | Designed for wind loads
Designed for notional loads
Stability system has been identified and evaluated to be adequate and robust
Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions or appropriate directions
Provided adequate internal and peripheral ties at floor levels
Designed for capacities to resist base overturning moment and base shear
Designed for building sway (p-delta effect)
Designed to limit overall lateral deflection of building using 3D modelling
Designed to limit inter-storey drift of building
Columns and walls have been checked for resistance to dynamic effects due to wind on the building
Checked for Requirements for Wind Tunnel Tests
Checked for long term lateral deflection of building under gravity load
Review the serviceability of the building due to dynamic performance
4 - Building with Specialised Structures | Building with Structural Steel Elements | Designed for bolted and welded connections of supports and member and splice joints | [6 empty] | 1 | 1 |  |  | 5
|  | Checked for in-plane and out-of-plane stability of frames | [6 empty] | 2 | 2 |  |  | 5
Designed for bracings and longitudinal ties for overall stability in both directon for both vertical and horizontal planes
|  | Designed for wind load on the building/structure | [10 empty] | 5
|  | Designed for lateral stability and torsional rigidity of structural elements and trusses | [6 empty] | 1 | 1 |  |  | 5
|  | Support conditions assumed in design have been checked against details provided | [6 empty] | 1 | 1 |  |  | 5
|  | Type of joint connections provided between members are consistent with joint rigidity adopted in the analysis and design | [6 empty] | 1 | 1 |  |  | 5
| Building with Precast Concrete Elements | All joint connections between precast members and precast to in-situ concrete members have been designed for during construction and permanent stages | [6 empty] | 1 | 1 |  |  | 5
|  | Loading conditions on precast members during erection or construction stage have been considered | [6 empty] | 1 | 1 |  |  | 2
Sufficient rigidity in the structural frame has been provided for to resist lateral loads
|  | Adequate internal & peripheral ties have been provided in floors | [6 empty] | 1 | 1 |  |  | 1
|  | All interface shear stresses have been checked | [10 empty] | 2
|  | Detailing of precast elements and structural joints have been checked | [6 empty] | 1 | 1 |  |  | 2
| Building with Prestressed Concrete Elements | Maximum prestress force and prestress losses for prestressed elements have been computed according to code requirements
Stresses for elements have been checked at transfer and service stages
Shear capacity has been designed for in prestressed elements
For transfer beams and long span beams, consideration of stage stressing has been made in design
End block design has been checked
Details of prestressed elements, tendon profile, etc. have been checked
| Buildings with Complex Structural Systems | Structural system with more than 2 transfer floor levels of which each carrying at least 3 floors; or structural system with cantilever transfer element carrying more than 5 floors
Inclined or curved building (offset of floor plate more than 3m from the edge of the floor above or below)
Structures with unconventional geometry (e.g. dome or arch-shaped)
Large span structures (with span more than 40m) or large cantilever span structures (where cantilever span is more than 8m)
Review construction sequence which may affect the load path
| Seismic Consideration | Determine the requirement for seismic consideration based on parameters such as soil type and building type. | [7 empty] | 1 |  |  | 5
|  | Analysis and design of additional loadcase on seismic requirement | [7 empty] | 1 |  |  | 5
|  | Review the movement of building under seismic to avoid impounding action | [7 empty] | 1 |  |  | 5
| Buildings with Basements | Basement construction method, i.e. top down construction, semi top down construction, bottom up construction
Proximity to sensitive structures such as underground tunnels or overhead viaduct
Check uplift on basement
Part basement construction with unbalanced lateral forces
Temporary conditions during basement construction affecting permanent design
5 - Earth Retaining Structures |  | Geotechnical parameters adopted for design of ERSS are consistent with site investigation report and published literature | [6 empty] | 1 | 1 |  |  | 5
|  | Analysis using 2D or 3D finite element method for ERSS. Number of sections for analysis in 2D method | [6 empty] | 1 | 2 |  |  | 10
Structure has been designed to resist overturning , sliding and bearing capacity failure
Structure has been designed to resist slip circle failure
Structure has been designed for onerous soil and water pressure acting on it
Adequate surcharge load has been taken into account in design
|  | ERSS checked for global stability, wall embedment, toe-stability, base heave and hydraulic uplift | [6 empty] | 1 | 1 |  |  | 5
Opening (service openings in wall), discontinuity in temporary retaining walls has been checked for stability.
|  | Comparison of member forces computation for walls, struts, waler and kingposts by QP & AC has been carried out. | [7 empty] | 1 |  |  | 2
|  | Impact assessment of ERSS to adjacent structures | [6 empty] | 1 | 2 |  |  | 5
|  | Instrumentation monitoring regime | [7 empty] | 0.5 |  |  | 1
6 - Specific Structural Elements |  | Slender Columns
Columns supporting transfer beams
Columns supporting long span beams
Columns supporting cantilever beams
Columns in a two column frame system
Cantilever beams
Long span beams
Transfer beams
Flat slabs/plates
Cantilevered structures with tie backs
Others
Summary of Resources and Fee ( | [6 empty] | TOTAL | 4 | 33 | 45.5 | 0 | 0 | 144 | 0 | 0 | 0 | 0
Resources |  | Total Hours | Unit rate* | Total Fee
Director / Principal |  | 4 | 0 | 0 |  |  | TOTAL | 226.5
Accredited Checker (if not director) |  | 33 | 0 | 0
Senior Associate Director |  | 45.5 | 0 | 0
Associate Director |  | 0 | 0 | 0
Senior Professional Staff (>10yrs) |  | 0 | 0 | 0
Professional Staff (<10yrs) |  | 144 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
|  | Raw Fee |  | 0
|  | Contingency | 10% | 0
|  | Final Fee |  | 0
|  | Manhours | 1812
* Refer to Standard Consultancy Agreement (SCA) for published recommended rates

## AC VAF Med C
Accredited Checker (AC) Value Articulation Framework (VAF) |  |  |  | version 0.2
Project |  | XYZ Project | By | Er ACES
Client |  | HDB | Date | 2026-09-01
Period |  | Jan 2027-Jan 2030
Category of Project |  | Medium - 3 Blocks of 30 storey HDB Building with 1 MSCP
[6 empty] | Program Unit | Hours | Resource Unit |  |  | Days
Project Stages |  | Tasks / Remarks | BCA Items of Services - Milestone (Reference to SCA) |  |  | Budget | Programme | Resources (Hours, Days, Weeks) | [9 empty] | Remarks
Stage | Sub-stage | Tasks / Remarks | ID | BCA Payment Milestone / Tasks | % fee | % of fee | Hours | Director / Principal | Accredited Checker (if not director) | Senior Associate Director | Associate Director | Senior Professional Staff (>10yrs) | Professional Staff (<10yrs)
0 - Project Mobilisation | Project preparation | Project Proposal and Setup including Quality and Verification Plan, Resource Plan, Work Breakdown Structure, Communication Plan | [5 empty] | 1 | 1 | 2 |  | 1 | 1
|  | Project team briefing and kick off | [5 empty] | 1 | 1 | 2 |  | 1 | 1
|  | Project Risk Assessment and Management plan | [5 empty] | 1 |  | 2 |  | 1 | 1
|  | Finance - Cashflow and invoicing plan | [5 empty] | 1 |  | 2 |  | 1 | 1
1 - Overall Design Review Tasks | Global Review of the Techincal Approach | Code of Practice | [6 empty] | 2 | 2 |  | 2 | 2
Design Loadings
Strucutral Analysis
Stability and Robustness
All Key Structural Elements
Architectural and Structural Drawings
Review of Soil report and Geotechnical Interpretation Report
Expert Reviewer is required
Other Aspects in Design
2 - Foundation design | Foundation Loads | Appropriate values of dead, live ,wind and notional loads have been used | [6 empty] | 1 | 1 |  | 2 | 10
|  | Column loads have been appropriately computed | [6 empty] | 3 | 3 |  | 10 | 40
|  | Effects of wind and notional loads on the building or structure have been checked | [6 empty] | 1 | 1 |  | 5 | 15
|  | Comparison of the loading computation by the QP & AC has been carried out | [6 empty] | 1 | 1 |  | 2 | 10
| Piles | Piles have been designed for skin friction and end bearing capacities | [6 empty] | 2 | 1 |  | 5 | 15
|  | Piles have been designed for lateral loads and bending moment | [6 empty] | 1 | 1 |  | 2 | 5
Pile joints have been designed for
|  | Piles have been designed for uplift | [6 empty] | 1 | 1 |  | 1 | 5
|  | Socketings have been designed for piles with short penetration depths | [6 empty] | 1 | 1 |  | 1 | 5
|  | Piles have been designed for negative skin friction | [6 empty] | 1 | 1 |  | 1 | 5
|  | Determine design pile settlement for building and impact on the main structures | [6 empty] | 1 | 1 |  | 2 | 5
| Raft/footing | Appropriate allowable bearing capacity of soil has been assumed in design | [6 empty] | 1 | 2 |  | 2 | 5
Appropriate modulus of sub-grade reaction of the soil has been assumed in design
Appropriate model used for structural analysis of the raft with appropriate loadings
The raft has been designed to resist punching shear from columns
|  | The building or structure has been designed to cater for probable differential and total settlement. | [6 empty] | 1 | 2 |  | 2 | 5
Review of plate load test results against design soil bearing capacity
3 - Building / Structural System | Building of less than 30 Storey | Designed for wind loads
Designed for notional loads
Stability system has been identified and evaluated to be adequate and robust
Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions
Provided adequate internal and peripheral ties at floor levels
Designed for capacities to resist base overturning moment and base shear
Designed for building sway (p-delta effect)
| Building of more than 30 storey | Designed for wind loads | [6 empty] | 5 | 5 |  | 10 | 40
Designed for notional loads
|  | Stability system has been identified and evaluated to be adequate and robust | [6 empty] | 1 | 1 |  | 3 | 10
|  | Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions or appropriate directions | [6 empty] | 1 | 1 |  | 2 | 5
|  | Provided adequate internal and peripheral ties at floor levels | [6 empty] | 1 | 1 |  | 2 | 5
|  | Designed for capacities to resist base overturning moment and base shear | [6 empty] | 1 | 1 |  | 2 | 5
|  | Designed for building sway (p-delta effect) | [6 empty] | 1 | 1 |  | 3 | 10
|  | Designed to limit overall lateral deflection of building using 3D modelling | [6 empty] | 3 | 3 |  | 5 | 10
|  | Designed to limit inter-storey drift of building | [6 empty] | 1 | 1 |  | 1 | 2
|  | Columns and walls have been checked for resistance to dynamic effects due to wind on the building | [6 empty] | 1 | 1 |  | 1 | 5
|  | Checked for Requirements for Wind Tunnel Tests | [6 empty] | 1 | 1 |  | 1 | 5
|  | Checked for long term lateral deflection of building under gravity load | [6 empty] | 1 | 1 |  | 1 | 5
|  | Review the serviceability of the building due to dynamic performance | [6 empty] | 2 | 2 |  | 5 | 5
4 - Building with Specialised Structures | Building with Structural Steel Elements | Designed for bolted and welded connections of supports and member and splice joints | [6 empty] | 1 | 1 |  | 5 | 10
|  | Checked for in-plane and out-of-plane stability of frames | [6 empty] | 1 | 1 |  | 5 | 10
Designed for bracings and longitudinal ties for overall stability in both directon for both vertical and horizontal planes
|  | Designed for wind load on the building/structure | [10 empty] | 2
|  | Designed for lateral stability and torsional rigidity of structural elements and trusses | [6 empty] | 1 | 1 |  | 2 | 5
|  | Support conditions assumed in design have been checked against details provided | [6 empty] | 1 | 1 |  | 1 | 5
|  | Type of joint connections provided between members are consistent with joint rigidity adopted in the analysis and design | [6 empty] | 1 | 1 |  | 1 | 5
| Building with Precast Concrete Elements | All joint connections between precast members and precast to in-situ concrete members have been designed for during construction and permanent stages | [6 empty] | 2 | 2 |  | 5 | 15
|  | Loading conditions on precast members during erection or construction stage have been considered | [6 empty] | 1 | 1 |  | 2 | 10
Sufficient rigidity in the structural frame has been provided for to resist lateral loads
|  | Adequate internal & peripheral ties have been provided in floors | [6 empty] | 1 | 1 |  | 2 | 10
|  | All interface shear stresses have been checked | [6 empty] | 1 | 1 |  | 1 | 5
|  | Detailing of precast elements and structural joints have been checked | [6 empty] | 1 | 1 |  | 2 | 10
| Building with Prestressed Concrete Elements | Maximum prestress force and prestress losses for prestressed elements have been computed according to code requirements
Stresses for elements have been checked at transfer and service stages
Shear capacity has been designed for in prestressed elements
For transfer beams and long span beams, consideration of stage stressing has been made in design
End block design has been checked
Details of prestressed elements, tendon profile, etc. have been checked
| Buildings with Complex Structural Systems | Structural system with more than 2 transfer floor levels of which each carrying at least 3 floors; or structural system with cantilever transfer element carrying more than 5 floors
Inclined or curved building (offset of floor plate more than 3m from the edge of the floor above or below)
Structures with unconventional geometry (e.g. dome or arch-shaped)
Large span structures (with span more than 40m) or large cantilever span structures (where cantilever span is more than 8m)
Review construction sequence which may affect the load path
| Seismic Consideration | Determine the requirement for seismic consideration based on parameters such as soil type and building type. | [6 empty] | 2 | 2 |  | 5 | 15
|  | Analysis and design of additional loadcase on seismic requirement | [7 empty] | 1 |  | 2 | 5
|  | Review the movement of building under seismic to avoid impounding action | [6 empty] | 1 | 1 |  | 2 | 5
| Buildings with Basements | Basement construction method, i.e. top down construction, semi top down construction, bottom up construction
Proximity to sensitive structures such as underground tunnels or overhead viaduct
Check uplift on basement
Part basement construction with unbalanced lateral forces
Temporary conditions during basement construction affecting permanent design
5 - Earth Retaining Structures |  | Geotechnical parameters adopted for design of ERSS are consistent with site investigation report and published literature | [6 empty] | 1 | 1 |  | 3 | 10
|  | Analysis using 2D or 3D finite element method for ERSS. Number of sections for analysis in 2D method | [6 empty] | 2 | 2 |  | 5 | 15
Structure has been designed to resist overturning , sliding and bearing capacity failure
Structure has been designed to resist slip circle failure
Structure has been designed for onerous soil and water pressure acting on it
Adequate surcharge load has been taken into account in design
|  | ERSS checked for global stability, wall embedment, toe-stability, base heave and hydraulic uplift | [6 empty] | 1 | 1 |  | 2 | 10
Opening (service openings in wall), discontinuity in temporary retaining walls has been checked for stability.
|  | Comparison of member forces computation for walls, struts, waler and kingposts by QP & AC has been carried out. | [6 empty] | 1 | 1 |  | 2 | 5
|  | Impact assessment of ERSS to adjacent structures | [6 empty] | 2 | 2 |  | 5 | 15
|  | Instrumentation monitoring regime | [6 empty] | 1 | 1 |  | 2 | 5
6 - Specific Structural Elements |  | Slender Columns
Columns supporting transfer beams
Columns supporting long span beams
Columns supporting cantilever beams
Columns in a two column frame system
Cantilever beams
Long span beams
Transfer beams
|  | Flat slabs/plates | [6 empty] | 1 | 1 |  | 5 | 15
Cantilevered structures with tie backs
Others
Summary of Resources and Fee | [6 empty] | TOTAL | 4 | 61 | 69 | 0 | 136 | 425 | 0 | 0 | 0 | 0
Resources |  | Total Hours | Unit rate* | Total Fee
Director / Principal |  | 4 | 0 | 0
Accredited Checker (if not director) |  | 61 | 0 | 0
Senior Associate Director |  | 69 | 0 | 0
Associate Director |  | 0 | 0 | 0
Senior Professional Staff (>10yrs) |  | 136 | 0 | 0
Professional Staff (<10yrs) |  | 425 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
|  | Raw Fee |  | 0
|  | Contingency | 10% | 0
|  | Final Fee |  | 0
|  | Manhours | 5560
* Refer to Standard Consultancy Agreement (SCA) for published recommended rates

## AC VAF High C
Accredited Checker (AC) Value Articulation Framework (VAF) |  |  |  | version 0.2
Project |  | XYZ Project | By | Er ACES
Client |  | HDB | Date | 2026-09-01
Period |  | Jan 2027-Jan 2030
Category of Project |  | High - 5 block of 50 Sotrey HDB Building with 1 MSCP and 1 basement
[6 empty] | Program Unit | Hours | Resource Unit |  |  | Days
Project Stages |  | Tasks / Remarks | BCA Items of Services - Milestone (Reference to SCA) |  |  | Budget | Programme | Resources (Hours, Days, Weeks) | [9 empty] | Remarks
Stage | Sub-stage | Tasks / Remarks | ID | BCA Payment Milestone / Tasks | % fee | % of fee | Hours | Director / Principal | Accredited Checker (if not director) | Senior Associate Director | Associate Director | Senior Professional Staff (>10yrs) | Professional Staff (<10yrs)
0 - Project Mobilisation | Project preparation | Project Proposal and Setup including Quality and Verification Plan, Resource Plan, Work Breakdown Structure, Communication Plan | [5 empty] | 2 | 1 | 2 | 2 | 2 | 2
|  | Project team briefing and kick off | [5 empty] | 2 | 1 | 2 | 2 | 2 | 2
|  | Project Risk Assessment and Management plan | [5 empty] | 2 |  | 2 | 2 | 2 | 2
|  | Finance - Cashflow and invoicing plan | [5 empty] | 2 |  | 2 | 2 | 2 | 2
1 - Overall Design Review Tasks | Global Review of the Techincal Approach | Code of Practice | [6 empty] | 2 | 2 | 2 | 2 | 2
|  | Design Loadings | [6 empty] | 1 | 1 | 1 | 1 | 1
|  | Strucutral Analysis | [6 empty] | 1 | 1 | 1 | 1 | 1
Stability and Robustness
|  | All Key Structural Elements | [6 empty] | 2 | 2 | 2 | 2 | 2
Architectural and Structural Drawings
|  | Review of Soil report and Geotechnical Interpretation Report | [6 empty] | 2 | 2 | 2 | 2 | 2
Expert Reviewer is required
Other Aspects in Design
2 - Foundation design | Foundation Loads | Appropriate values of dead, live ,wind and notional loads have been used | [6 empty] | 2 | 2 | 5 | 10 | 20
|  | Column loads have been appropriately computed | [6 empty] | 5 | 5 | 10 | 25 | 60
|  | Effects of wind and notional loads on the building or structure have been checked | [6 empty] | 2 | 2 | 5 | 15 | 30
|  | Comparison of the loading computation by the QP & AC has been carried out | [6 empty] | 1 | 1 | 5 | 10 | 20
| Piles | Piles have been designed for skin friction and end bearing capacities | [6 empty] | 5 | 5 | 10 | 25 | 40
|  | Piles have been designed for lateral loads and bending moment | [6 empty] | 1 | 1 | 2 | 5 | 15
Pile joints have been designed for
|  | Piles have been designed for uplift | [6 empty] | 1 | 1 | 2 | 5 | 15
|  | Socketings have been designed for piles with short penetration depths | [6 empty] | 1 | 1 | 2 | 5 | 15
|  | Piles have been designed for negative skin friction | [6 empty] | 1 | 1 | 2 | 5 | 10
|  | Determine design pile settlement for building and impact on the main structures | [6 empty] | 1 | 1 | 2 | 5 | 15
| Raft/footing | Appropriate allowable bearing capacity of soil has been assumed in design | [6 empty] | 2 | 2 | 2 | 5 | 15
Appropriate modulus of sub-grade reaction of the soil has been assumed in design
Appropriate model used for structural analysis of the raft with appropriate loadings
The raft has been designed to resist punching shear from columns
|  | The building or structure has been designed to cater for probable differential and total settlement. | [6 empty] | 2 | 2 | 2 | 5 | 15
Review of plate load test results against design soil bearing capacity
3 - Building / Structural System | Building of less than 30 Storey | Designed for wind loads
Designed for notional loads
Stability system has been identified and evaluated to be adequate and robust
Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions
Provided adequate internal and peripheral ties at floor levels
Designed for capacities to resist base overturning moment and base shear
Designed for building sway (p-delta effect)
| Building of more than 30 storey | Designed for wind loads | [6 empty] | 10 | 10 | 20 | 40 | 80
Designed for notional loads
|  | Stability system has been identified and evaluated to be adequate and robust | [6 empty] | 2 | 2 | 2 | 5 | 20
|  | Designed corewalls and columns to resist lateral loads due to wind and notional loads in both directions or appropriate directions | [6 empty] | 5 | 5 | 10 | 20 | 40
|  | Provided adequate internal and peripheral ties at floor levels | [6 empty] | 1 | 1 | 5 | 10 | 20
|  | Designed for capacities to resist base overturning moment and base shear | [6 empty] | 1 | 1 | 5 | 10 | 20
|  | Designed for building sway (p-delta effect) | [6 empty] | 1 | 1 | 5 | 10 | 20
|  | Designed to limit overall lateral deflection of building using 3D modelling | [6 empty] | 3 | 3 | 10 | 10 | 20
|  | Designed to limit inter-storey drift of building | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Columns and walls have been checked for resistance to dynamic effects due to wind on the building | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Checked for Requirements for Wind Tunnel Tests | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Checked for long term lateral deflection of building under gravity load | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Review the serviceability of the building due to dynamic performance | [6 empty] | 3 | 3 | 10 | 10 | 20
4 - Building with Specialised Structures | Building with Structural Steel Elements | Designed for bolted and welded connections of supports and member and splice joints | [6 empty] | 1 | 1 | 5 | 10 | 20
|  | Checked for in-plane and out-of-plane stability of frames | [6 empty] | 2 | 2 | 10 | 20 | 40
Designed for bracings and longitudinal ties for overall stability in both directon for both vertical and horizontal planes
|  | Designed for wind load on the building/structure | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Designed for lateral stability and torsional rigidity of structural elements and trusses | [6 empty] | 5 | 5 | 10 | 15 | 30
|  | Support conditions assumed in design have been checked against details provided | [6 empty] | 1 | 1 | 1 | 1 | 5
|  | Type of joint connections provided between members are consistent with joint rigidity adopted in the analysis and design | [6 empty] | 1 | 1 | 1 | 1 | 5
| Building with Precast Concrete Elements | All joint connections between precast members and precast to in-situ concrete members have been designed for during construction and permanent stages | [6 empty] | 2 | 2 | 5 | 15 | 30
|  | Loading conditions on precast members during erection or construction stage have been considered | [6 empty] | 1 | 1 | 2 | 5 | 15
Sufficient rigidity in the structural frame has been provided for to resist lateral loads
|  | Adequate internal & peripheral ties have been provided in floors | [6 empty] | 2 | 2 | 2 | 5 | 10
|  | All interface shear stresses have been checked | [6 empty] | 1 | 1 | 1 | 2 | 5
|  | Detailing of precast elements and structural joints have been checked | [6 empty] | 2 | 2 | 5 | 10 | 20
| Building with Prestressed Concrete Elements | Maximum prestress force and prestress losses for prestressed elements have been computed according to code requirements
Stresses for elements have been checked at transfer and service stages
Shear capacity has been designed for in prestressed elements
For transfer beams and long span beams, consideration of stage stressing has been made in design
End block design has been checked
Details of prestressed elements, tendon profile, etc. have been checked
| Buildings with Complex Structural Systems | Structural system with more than 2 transfer floor levels of which each carrying at least 3 floors; or structural system with cantilever transfer element carrying more than 5 floors
Inclined or curved building (offset of floor plate more than 3m from the edge of the floor above or below)
Structures with unconventional geometry (e.g. dome or arch-shaped)
Large span structures (with span more than 40m) or large cantilever span structures (where cantilever span is more than 8m)
Review construction sequence which may affect the load path
| Seismic Consideration | Determine the requirement for seismic consideration based on parameters such as soil type and building type. | [6 empty] | 2 | 2 | 5 | 10 | 20
|  | Analysis and design of additional loadcase on seismic requirement | [6 empty] | 1 | 1 | 2 | 5 | 10
|  | Review the movement of building under seismic to avoid impounding action | [6 empty] | 1 | 1 | 2 | 5 | 10
| Buildings with Basements | Basement construction method, i.e. top down construction, semi top down construction, bottom up construction | [6 empty] | 5 | 5 | 10 | 15 | 30
|  | Proximity to sensitive structures such as underground tunnels or overhead viaduct | [6 empty] | 2 | 2 | 2 | 5 | 10
|  | Check uplift on basement | [6 empty] | 1 | 1 | 1 | 2 | 5
Part basement construction with unbalanced lateral forces
|  | Temporary conditions during basement construction affecting permanent design | [6 empty] | 2 | 2 | 2 | 5 | 10
5 - Earth Retaining Structures |  | Geotechnical parameters adopted for design of ERSS are consistent with site investigation report and published literature | [6 empty] | 2 | 2 | 5 | 10 | 20
|  | Analysis using 2D or 3D finite element method for ERSS. Number of sections for analysis in 2D method | [6 empty] | 5 | 5 | 10 | 15 | 30
Structure has been designed to resist overturning , sliding and bearing capacity failure
Structure has been designed to resist slip circle failure
Structure has been designed for onerous soil and water pressure acting on it
Adequate surcharge load has been taken into account in design
|  | ERSS checked for global stability, wall embedment, toe-stability, base heave and hydraulic uplift | [6 empty] | 2 | 2 | 5 | 10 | 20
Opening (service openings in wall), discontinuity in temporary retaining walls has been checked for stability.
|  | Comparison of member forces computation for walls, struts, waler and kingposts by QP & AC has been carried out. | [6 empty] | 2 | 2 | 5 | 10 | 20
|  | Impact assessment of ERSS to adjacent structures | [6 empty] | 2 | 2 | 5 | 10 | 20
|  | Instrumentation monitoring regime | [6 empty] | 1 | 1 | 1 | 5 | 10
6 - Specific Structural Elements |  | Slender Columns
Columns supporting transfer beams
Columns supporting long span beams
Columns supporting cantilever beams
Columns in a two column frame system
Cantilever beams
Long span beams
Transfer beams
|  | Flat slabs/plates | [6 empty] | 2 | 2 | 10 | 15 | 30
Cantilevered structures with tie backs
Others
Summary of Resources and Fee | [6 empty] | TOTAL | 8 | 113 | 119 | 244 | 462 | 976 | 0 | 0 | 0 | 0
Resources |  | Total Hours | Unit rate* | Total Fee
Director / Principal |  | 8 | 0 | 0
Accredited Checker (if not director) |  | 113 | 0 | 0
Senior Associate Director |  | 119 | 0 | 0
Associate Director |  | 244 | 0 | 0
Senior Professional Staff (>10yrs) |  | 462 | 0 | 0
Professional Staff (<10yrs) |  | 976 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
0 |  | 0 | 0 | 0
|  | Raw Fee |  | 0
|  | Contingency | 10% | 0
|  | Final Fee |  | 0
|  | Manhours | 15376
* Refer to Standard Consultancy Agreement (SCA) for published recommended rates